## Slide 1: NIRS prediction modeling and association mapping for biochemical traits related to malting in barley
Shakti Khera
1800264RSP
PhD Scholar
Post comprehensive(14) SRC Meeting
Supervisor – Dr. S.B. Tripathi
Department of Biotechnology
TERI SAS
Co-Supervisor – Dr. Rakesh Bhardwaj
Department of Germplasm Evaluation
ICAR-NBPGR

## Slide 2
SRC Members
Dr. Shashi Bhushan Tripathi (Supervisor)
Dr. Rakesh Bhardwaj, NBPGR (Co-supervisor)
Dr. Anandita Singh
Dr. Chaithanya Madhurantakam

## Slide 3: Objectives
Developing NIRS calibration models for selected biochemical traits related to malting in barley.
Identification of SNPs associated with select biochemical traits related to malting.

## Slide 4: Timelines
Objective | Activity | Years |  |  |  |  | 
 |  | 1-2 | 2-3 | 3-4 | 4-5 | 5-6 | 6-7
I | Sample acquisition |  |  |  |  |  | 
 | NIR spectra acquisition of all the samples |  |  |  |  |  | 
 | Selection of diverse germplasm |  |  |  |  |  | 
 | Chemical analysis of representative set |  |  |  |  |  | 
 | Development of NIRS prediction model |  |  |  |  |  | 
 | Validation of NIRS prediction model |  |  |  |  |  | 
II | GBS of selected elite lines (~100 accessions) |  |  |  |  |  | 
 | Association mapping for targeted traits |  |  |  |  |  | 
Yet to be initiated
Ongoing
Completed

## Slide 5: Work done (January 2025 to June 2025)
GWAS analysis Completed
Revision of manuscript for submission with Cereal Chemistry
Draft Thesis for submission

## Slide 6
Thank You